## Risk Register
Task 4.2 — Risk Register & Controls Documentation
Target: OWASP Juice Shop lab ¦ Based on findings from Task 4.1 Structured Security Assessment
Risk ID | Finding | Likelihood | Impact | Risk Rating | Risk Description | Recommended Control | Control Type | Owner
R-01 | SQL Injection (login bypass) — F-01 | High | Severe | Critical | Login form accepts raw SQL in input, allowing full authentication bypass without valid credentials. | Use parameterized queries/prepared statements for all database calls; apply strict input validation on login fields. | Preventive | Dev Team
R-02 | Cross-Site Scripting (XSS) — F-02 | Medium | High | High | Search field renders unsanitized HTML/JS, allowing arbitrary script execution in a victim's browser. | Sanitize and encode all user input before rendering to the DOM; implement a strict Content-Security-Policy. | Preventive | Dev Team
R-03 | Insecure session/token handling — F-03 | Medium | High | High | Session JWT cookie lacks HttpOnly, Secure, and SameSite flags, making it readable by scripts and interceptable over HTTP. | Set HttpOnly, Secure, and SameSite=Strict/Lax flags on all session cookies. | Preventive | Dev Team
R-04 | Exposed directory with sensitive files (/ftp) — F-04 | High | High | High | The /ftp path is publicly browsable and exposes files that appear to contain credentials, legal documents, and backups. | Disable directory listing; move sensitive files out of the web root or restrict access with authentication. | Preventive | Dev/Infra Team
R-05 | Missing Content-Security-Policy header — F-05 | Medium | Medium | Medium | Without a CSP, the browser has no restriction on what an injected script (e.g. via XSS) is allowed to do. | Implement a Content-Security-Policy header restricting script sources to trusted origins only. | Preventive | Dev Team
R-06 | Wildcard CORS policy — F-06 | Medium | Medium | Medium | Access-Control-Allow-Origin: * permits any external domain to make requests to the application's API. | Restrict CORS to a defined allow-list of trusted origins instead of a wildcard. | Preventive | Dev Team
R-07 | Information disclosure via robots.txt — F-07 | Low | Low | Low | robots.txt lists a disallowed /ftp path, inadvertently revealing its existence to anyone who checks the file. | Avoid listing sensitive paths in robots.txt; rely on proper access control rather than obscurity. | Preventive | Dev Team
R-08 | Unexpected open port (34979) — F-08 | Low | Low | Low | An unrelated Golang HTTP service is listening on the host, unnecessarily increasing the attack surface. | Identify the service, disable it if not required, and restrict/firewall any non-essential open ports. | Preventive | Infra Team
Summary
Total risks logged: | 8
Critical: | 1
High: | 3
Medium: | 2
Low: | 2

## Risk Matrix Guide
Risk Rating Matrix (Likelihood x Impact)
| Low Impact | Medium Impact | High Impact / Severe
High Likelihood | Medium | High | Critical
Medium Likelihood | Low | Medium | High
Low Likelihood | Low | Low | Medium